## Sheet1
Task | Estimated time | Actual time | status
csvHandler.py
read csv file | 0.25 | 0.25 | completed
readline csv file | 0.25 | 0.25 | completed
append into csv file | 0.25 | 0.25 | completed
write into csv file | 0.25 | 0.25 | completed
MenuFun.py
completed
import module | 0.25 | 0.25 | completed
cheack book_id | 3 | 3 | completed
adding function | 6 | 4 | completed
searching function | 6 | 4 | completed
editing function | 8 | 2 | completed
deleting function | 8 | 8 | completed
display function | 1 | 1 | completed
labrary menu program.py
import module | 0.25 |  | completed
create menu | 0.25 |  | completed
calling function | 0.25 |  | completed
Total hours | 34 | 23.25