## Sheet1
Sr no | Task Assigned | Estimited time | Actual Time | Status
1 | Readlines in csv file | 0.25 | 0.25 | completed
2 | Append into csv file | 0.25 | 0.25 | completed
3 | Write into csv file | 0.25 | 0.25 | completed
4 | List cleaning method | 0.5 | 0.5 | completed
5 | checking Employee_id method | 0.75 | 0.75 | completed
6 | Create class and object | 1 | 0.75 | completed
7 | constructor method passing employee details | 2 | 2 | completed
8 | Adding menu option | 3 | 5 | finding some error and solve it using oops. completed
9 | Search search by employee id, searching by name menu option | 7 | 8 | completed
10 | Display menu option | 2 | 1.75 | completed
11 | Editing menu option | 8 | 28 | finding some error. And solve it using oops. Completed.
12 | Deleting menu option | 7 | 15.5 | finding some error. and try to solve it using oops. Completed
13 | create Menu | 0.25 | 0.25 | completed
14 | calling function | 0.25 | 0.25 | completed
| Total hours | 32.5 | 63.5
Sr no | Task Assigned | Estimited time | Actual Time | Status
1 | Learn tkinter | 8 | 23 | Title, icon, Label, Grid, place, entry widget, Button, maxsize, minsize,list box, canvas, progress bar, Photo Image, scroll bar, Menu, Menu Button, option Menu, scale, colorchooser, filedialog, savefile, OpenFile,Tcl. Completed
2 | create menu | 1
a. | Adding function | 3 | 5 | completed
b. | display function | 3
c. | delete function | 3
d. | search function | 5 | 6 | in-progress
e. | modify function | 6
3 | Csv Handler
a. | read data into csv file | 0.5
b. | Append data into csv file | 0.5 | 1.5 | completed
c. | write data into csv file | 0.5 | 1.5 | completed
4 | GUI
a. | adding data from | 3 | 3 | completed
b. | editing from | 4 | 1 | in-progress
c. | delete from | 4
d. | searching from | 4 | 5 | completed
| Total hours | 45.5 | 40
Sr no | Task Assigned | Estimited time | Actual Time | Status
|  | 8 | 23 | Title, icon, Label, Grid, place, entry widget, Button, maxsize, minsize,,combo box, check button, radio button, frame, message box(showinfo,showwarning,showerror,askretrycancel,askyesno,askyesnocancel),list box, canvas, progress bar, Photo Image, scroll bar, Menu, Menu Button, option Menu, scale, colorchooser, filedialog, savefile, OpenFile,Tcl. completed
2 | create menu | 1
a. | Adding | 3 | 6 | completed
b. | display | 3
c. | delete | 3
d. | search | 5 | 6 | completed
e. | modify | 6 | 6 | in-progress
3 | Csv Handler
a. | read data into csv file | 0.5 | 1 | completed
b. | Append data into csv file | 0.5 | 1 | completed
c. | write data into csv file | 0.5 | 1 | completed
4 | All menu option GUI file operation | 10 | 14 | Adding from, searching from completed, other option in-progress
| Total hours | 40.5 | 58