## Sheet1
Sr no | Task Assigned | Estimited time | Actual Time | Status
1 | Readlines in csv file | 0.25 | 0.25 | completed
2 | Append into csv file | 0.25 | 0.25 | completed
3 | Write into csv file | 0.25 | 0.25 | completed
4 | List cleaning method | 0.5 | 0.5 | completed
5 | checking Employee_id method | 0.75 | 0.75 | completed
6 | Create class and object | 1 | 0.75 | completed
7 | constructor method passing employee details | 2 | 2 | completed
8 | Adding menu option | 3 | 5 | finding some error and solve it completed
9 | Search search by employee id, searching by name menu option | 7 | 8 | completed
10 | Display menu option | 2 | 1.75 | completed
11 | Editing menu option | 8 | 24 | finding some error. And solve it using oops. Testing in-progress
12 | Deleting menu option | 7 | 8.5 | finding some Error. In-progress
13 | create Menu | 0.25 | 0.25 | completed
14 | calling function | 0.25 | 0.25 | completed
| Total hours | 32.5 | 52.5